## Slide 1: Discharge Flow Programme Closure Report
30 September 2026

## Slide 2: Programme Closure Summary
Programme Overview and Reason for Closure
Aim: 33% of discharges before midday on 8 medical wards and 0.5 days off average length of stay by September 2026. Closing as planned: CITI support ends and the work is handed to the Clinical Group.
Key Programme Outputs and Suggested Next Steps | Key Programme Outputs and Suggested Next Steps |  |  | Deliverables status and suggested next steps | 
Workstream | Key outputs | Relevant documents | Status | Handover owner | Suggested next steps / outstanding activities to be undertaken
Board rounds & CLD | Board round standard; role cards; CLD policy | Teams: Board round SOP | Complete | Joy Adebayo | Quarterly audit; spread to surgical wards
TTOs & pharmacy | TTO process; 2 technician posts; TTO tracker | Teams: TTO SOP; tracker guide | Complete | Leila Haddad | Agree weekend technician cover
Transport & lounge | Morning bookings; lounge from 8am | Teams: Lounge standard | Complete | Kwame Asante | Review transport contract in 2027
Complex discharges | Daily transfer of care huddle; D2A pilot | Teams: Huddle terms of reference | Partly complete | Fiona Gallagher | Finish D2A evaluation (Nov)
Data | Discharge dashboard with SPC charts | Teams: Dashboard user guide | Complete | Omar Siddiqui | Move to the Trust BI platform
PMO & comms | Patient leaflet; case study; this report | Teams: Comms plan; RAID log | Complete | Ruth Adeyemi | Archive the Teams site in Dec
 |  | [Link to docs on teams] |  |  | 
Key Achievements
Discharges before midday up from 16% to 31%
Length of stay down from 7.4 to 6.9 days
TTO ready time down from 4.2 to 2.1 hours
No rise in readmissions
Sustainability plan
Owned by Grace Mensah (General Manager). Weekly SPC charts at the Medicine Operational Group; quarterly Flow Manual audit; ward champions on every ward.
V1 October 2022

## Slide 3: Programme Benefits Realisation
Workstream | Benefit | Type | Baseline performance (pre-programme) | Target performance | Current performance | Comment
Original Programme Benefits | Original Programme Benefits |  |  |  |  | 
Board rounds | More discharges before midday | Flow | 16% | 33% | 31% | Close to target; still improving
All | Shorter length of stay | Efficiency | 7.4 days | 6.9 days | 6.9 days | Met; about 3,000 bed days a year
TTOs | Faster TTOs | Quality | 4.2 hours | 2.0 hours | 2.1 hours | Close to target
Transport & lounge | More use of the discharge lounge | Efficiency | 12% | 40% | 38% | Close to target
Board rounds | EDD set within 24 hours | Quality | 41% | 90% | 88% | Close to target
All | No rise in readmissions (balancing) | Safety | 13.8% | No rise | 13.5% | Met
Additional Programme Benefits | Additional Programme Benefits |  |  |  |  | 
Complex discharges | Fewer patients waiting over 7 days for social care | Experience | 34 a week | - | 22 a week | Not planned; came from the daily huddle
V1 October 2022

## Slide 4: Ongoing Programme Risks and Issues
Risks |  |  |  |  |  |  |  |  |  |  |  | 
Ref # | Date Raised | Owner | Workstream | Description | Likelihood (1-5) | Impact (1-5) | Exposure (L*I) | Mitigation Actions | Likelihood (1-5) | Impact (1-5) | Exposure (L*I) | Status - commentary
R-007 | 02/09/26 | Grace Mensah | Board rounds | Gains slip once CITI support ends | 3 | 4 | 12 | Ward champions; quarterly audit; SPC review monthly | 2 | 4 | 8 | Handed to Clinical Group
R-008 | 02/09/26 | Leila Haddad | TTOs | No weekend technician cover | 3 | 3 | 9 | Bid in 2027/28 planning round | 2 | 3 | 6 | Open
Issues |  |  |  |  |  |  | 
Ref # | Date Raised | Owner | Workstream | Description | Impact (1-5) | Actions to resolve | Status - commentary
I-006 | 09/09/26 | Fiona Gallagher | Complex discharges | D2A pilot evaluation not finished | 2 | Finish evaluation with local authority by November | Handed to discharge team
V1 October 2022

## Slide 5: Feedback
Stakeholder | Feedback
Ward 6 manager | “The morning board round is now just how we do it. We don't need CITI in the room any more.”
Consultant physician | “Criteria-led discharge took a while to trust, but it saves me a ward round most days.”
Lead pharmacist | “Having technicians on the wards changed the relationship with ward teams completely.”
Patient panel | “Being told the day before what time I'd go home made a real difference to my family.”
Local authority partner | “The daily huddle means we hear about complex patients days earlier.”
V1 October 2022

## Slide 6: Lessons learnt
Reflection Area | Lessons Learnt
Did we achieve the objectives of the project and if not, why not? | Mostly: the length of stay aim was met and discharges before midday reached 31% against 33%. Wards 1 to 4 started later because of rota gaps.
What worked well and why? | Starting on 2 wards and spreading: other wards saw it working. Weekly SPC charts at ward huddles kept attention on the data.
What could we have done better? | Agree the data definitions in mobilisation. We lost 3 weeks fixing ward codes in the TTO tracker.
What were the key challenges and how could they have been avoided? | Junior doctor rota gaps. Earlier escalation to the Clinical Director would have helped.
Did we use any innovative approaches or best practice techniques during the programme and if so, how did they work? | Ward 'Big Rooms' and criteria-led discharge worked well. The patient panel shaped the leaflet.
Did the team have the right resources and were there any skills that were missing? | Mostly; we were short of analyst time in mobilisation.
Are there any improvement suggestions regarding the methods, tools and templates used to develop the programme? | The highlight report template worked well; the RAID log was too long to review weekly, so we filtered to red and amber.
Other [as relevant] | Share the board round standard with surgical wards first.
V1 October 2022

## Slide 7: Programme Case Study
Programme Overview
Patients on our medical wards wait most of the day to go home: only 16% leave before midday, so A&E patients wait for beds into the evening. We will redesign the discharge day with ward teams, pharmacy and transport so patients who are ready go home in the morning.
Key Achievements and Benefits Realised
31% of discharges before midday (from 16%)
0.5 days off average length of stay
About 3,000 bed days a year released
TTOs ready in 2.1 hours (from 4.2)
No rise in readmissions
Approach
Started on Wards 5 and 6 and spread ward by ward with Plan, Do, Study, Act cycles
Morning board rounds with criteria-led discharge
TTOs written the day before, with technicians on the wards
Lounge open from 8am and morning transport bookings
Daily transfer of care huddle with social work
Weekly SPC charts at every ward huddle
V1 October 2022