## Slide 1
 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026
Board rounds & CLD |  |  |  |  |  | 
TTOs & pharmacy |  |  |  |  |  | 
Transport & lounge |  |  |  |  |  | 
Complex discharges |  |  |  |  |  | 
Data |  |  |  |  |  | 
PMO & comms |  |  |  |  |  | 
V1 October 2022
Critical Path
Milestone
Project plan on a page
A high level summary of the Discharge Flow Programme from March to August 2026, by workstream, with its milestones. The critical path is the sequence of tasks that must finish on time for the programme to finish on time.
Test on Wards 5 and 6
Spread to all 8 wards
Embed and audit
TTO the day before
Technicians on wards
Morning transport bookings
Lounge from 8am
Daily transfer of care huddle
Discharge to assess
Baseline
Weekly SPC charts
Launch
Ward roadshows
Handover and closure
First daily huddle
Baseline agreed
Launch event
Wards 5 and 6 tested
Technicians in post
Lounge opens at 8am
All 8 wards live
Weekend cover agreed
Handover to Clinical Group