## Summary (hidden)
Major Programmes Risks, Actions, Issues, Dependencies and Opportunities (RAIDO)
This document supports the MP Integrated Overview plan. To document the key risks, milestones and dependencies that have been identified.
What is the document used for?
This document is managed in conjunction with the Major Programmes to document the delivery status and to identify key issues that need to go to the attention of the TMP E and B.
Who manages this document?
The document is managed and owned by the MPO Business Partners, with each Business Partner being responsible for updating information related to their programme.
MPO Business Partners Alignment
a. Kathryn Ascroft - Evelina, RBH-KHP Partnership Programme and Merger Integration Programme, Trust Operating Model
b. Lucy Oliver - Pathology and Apollo
Dated: 10th March 2021
Version: DRAFT_0.1
Major Programmes
Risks, Issues, Dependency's, Milestones and Business Change
(Programme Documents)
Major Programmes Office
High Impact Risks, Issues, and Critical Dependencies and Milestones and Significant Change.
(MPO RAIDO)
Managed through the BP Fortnightly 1:1 Sessions
TMP
Escalations for consideration
(TMP Reports)
Rules/Principles for inclusion into the MPO RAIDO
1. High Impact Major Programme Risks and Issues (Risks scoring 12 and over post mitigation)
2. High Impact Risk and Issues that would have wider trust impact
3. Major Programme Critical Milestones
4. Significant Release of Change into the Trust
5. Dependencies that directly impact the delivery of a critical milestone or a important release of change

## Cover
V1 October 2022
Project: | Discharge Flow Programme
Project Manager: | James Holloway, Senior Improvement Manager, CITI
RISKS, ASSUMPTIONS, ISSUES AND
DEPENDENCIES (RAID) LOG

## Risks
RISKS
| Date of last review | 2026-05-11
[8 empty] | Pre Mitigation Impact Assessment |  |  |  | Post Mitigation Impact Assessment
| Ref # | Date Raised | Owner | Responsible | Workstream | Title | Description | Likelihood (1-5) | Impact (1-5) | Exposure (L*I) | Mitigation Actions | Likelihood (1-5) | Impact (1-5) | Exposure (L*I) | Trend | Impact Date | Status | Status - commentary | Date closed | Escalate to Exec
| R-001 | 2026-02-09 | Tom Reid | Grace Mensah | Board rounds and criteria-led discharge | Bed pressures | If winter-level bed pressures continue into spring, ward staff will miss board round training and the spread will slip. | 4 | 4 |  | Train in 30-minute slots at the ward huddle; matrons protect time; start with 2 wards. | 3 | 4 |  | Up | 2026-04-30 | Open | Pressures continued into May; escalated to leadership meeting 14/05. |  | Yes
| R-002 | 2026-02-09 | Dr Amara Okafor | Leila Haddad | Medicines to take out (TTOs) | Business case delay | If the pharmacy technician business case is delayed, TTOs will still wait for dispensary staff. | 3 | 4 |  | Take to the March investment panel; agree interim bank cover. | 2 | 3 |  | Down | 2026-03-31 | Closed | Approved 18/03; both posts filled 05/05. | 2026-05-05 | No
| R-003 | 2026-02-23 | Leila Haddad | Arjun Mehta | Medicines to take out (TTOs) | Technicians pulled away | If dispensary is short-staffed, ward technicians will be pulled back and TTO times will rise. | 3 | 3 |  | Agree a minimum ward cover rule with the pharmacy manager. | 2 | 3 |  | No Change | 2026-06-30 | Open | Rule agreed 28/04; happened twice in May. |  | No
| R-004 | 2026-03-02 | Kwame Asante | Kwame Asante | Transport and discharge lounge | Transport capacity | If the provider cannot add morning vehicles, patients will wait in the lounge until the afternoon. | 3 | 3 |  | Share daily booking forecasts with the provider; review at the monthly contract meeting. | 2 | 3 |  | Down | 2026-04-30 | Open | Morning slots up from 6 to 10 a day. |  | No
| R-005 | 2026-03-02 | Fiona Gallagher | Martin Doyle | Complex discharges | Social work input | If the local authority cannot staff the daily huddle, complex discharges will not move earlier. | 2 | 4 |  | Agree named social workers and a deputy rota. | 2 | 3 |  | No Change | 2026-05-31 | Open | Running daily since 13/04. |  | No
| R-006 | 2026-03-16 | James Holloway | Omar Siddiqui | Data and measurement | Data quality | If ward codes are wrong in the TTO data, the tracker will show the wrong wards' times. | 3 | 2 |  | Check codes against bed management each week. | 1 | 2 |  | Down | 2026-04-30 | Closed | Merged into issue I-002. | 2026-04-22 | No
R-007
R-008
R-009
R-010
R-011
R-012
R-013
R-014
R-015
R-016
R-017
R-018
R-019
R-020
R-021
R-022
R-023
R-024
R-025

## Issues
ISSUES
| Date of last review | 2026-05-11
| Ref # | Date Raised | Owner | Responsible | Workstream | Title | Description | Impact (1-5) | Actions to resolve | Trend | Status | Status - commentary | Date closed | Escalate to Exec
| I-001 | 2026-04-20 | Dr Sofia Marquez | Grace Mensah | Medicines to take out (TTOs) | Junior doctor rota gaps | Rota gaps on Wards 1 to 4 mean TTOs are not written the day before. | 4 | Clinical Director to raise with the rota team; decision on locum cover at leadership meeting. | Up | Open | Escalated 14/05. |  | Yes
| I-002 | 2026-04-22 | Omar Siddiqui | Omar Siddiqui | Data and measurement | Tracker ward codes | Wards 2 and 3 have the wrong codes in the TTO tracker. | 2 | Fix the codes with Digital; back-fill April data. | No Change | Open | Fix due 22/05. |  | No
| I-003 | 2026-04-06 | Kwame Asante | Joy Adebayo | Transport and discharge lounge | Lounge chairs | 2 of 12 lounge chairs broken, so the lounge fills by 11am. | 2 | Estates to replace from the capital budget. | Down | Closed | Replaced 24/04. | 2026-04-24 | No
I-004
I-005
I-006
I-007
I-008
I-009
I-010
I-011
I-012
I-013
I-014
I-015
I-016
I-017
I-018
I-019
I-020
I-021
I-022
I-023
I-024
I-025

## Assumptions
ASSUMPTIONS
| Date of last review | 2026-05-11
| Ref # | Date Raised | Forum raised by | Assumption Title | Assumption Description | Impact of Assumption | Workstream | Owner | Priority | Status
| AS-001 | 2026-02-02 | Mobilisation workshop | Ward time | Ward teams can free 2 hours a week each for the programme. | If not, the spread to 8 wards takes longer. | Board rounds and criteria-led discharge | Grace Mensah | High | Open
| AS-002 | 2026-02-02 | Mobilisation workshop | Transport at no cost | The transport provider can take more morning bookings within the current contract. | If not, we need a contract change (3 months). | Transport and discharge lounge | Kwame Asante | Medium | Closed
| AS-003 | 2026-02-09 | Leadership meeting | Data available | Discharge times can be taken daily from the patient record. | If not, the dashboard is weekly and manual. | Data and measurement | Omar Siddiqui | Medium | Closed
| AS-004 | 2026-02-09 | Leadership meeting | Readmissions stable | Earlier discharge does not raise readmissions; we track this as a balancing measure. | If readmissions rise, we pause and review. | Board rounds and criteria-led discharge | Dr Sofia Marquez | High | Open
AS-005
AS-006
AS-007
AS-008
AS-009
AS-010
AS-011
AS-012
AS-013
AS-014
AS-015
AS-016
AS-017
AS-018
AS-019
AS-020
AS-021
AS-022
AS-023
AS-024
AS-025

## Dependencies
DEPENDENCIES
| Date of last review | 2026-05-11
| Ref # | Date Raised | Workstream affected | Who is dependent on Delivery? | Who is Responsible for Delivery? | Summary Description | Delivery date | Status | Status commentary | RAG | Priority
| DEP-001 | 2026-02-09 | Board rounds and criteria-led discharge | Board rounds workstream | Digital (patient record team) | EDD field in the board round view | 2026-06-30 | Agreed | In the June release | A | High
| DEP-002 | 2026-02-09 | Complex discharges | Complex discharges workstream | Local authority social work | Named social workers for the daily huddle | 2026-04-13 | Delivered | Live 13/04 | G | High
| DEP-003 | 2026-03-16 | Transport and discharge lounge | Transport and lounge workstream | Estates | Lounge refurbishment and 4 extra chairs | 2026-04-30 | Delivered late | Done 06/05 | G | Medium
| DEP-004 | 2026-03-16 | Board rounds and criteria-led discharge | Whole programme | UEC Programme | Same day emergency care changes, so admissions don't rise | 2026-07-31 | Meeting planned | Next UEC board 21/05 | A | Medium
DEP-005
DEP-006
DEP-007
DEP-008
DEP-009
DEP-010
DEP-011
DEP-012
DEP-013
DEP-014
DEP-015
DEP-016
DEP-017
DEP-018
DEP-019
DEP-020
DEP-021
DEP-022
DEP-023
DEP-024
DEP-025
Note on F6: This should be the name of the person who the delivering party should reach agreement with

## Definitions and Validation
Definitions
The RAID Log contains four different Logs that include Risks, Assumptions, Issues and Dependencies.
Each log is oriented to have a clear description of each item in them taking into account the following definitions:
Risk | We define a risk as a potential situation that could impact the programme (positively or negatively) in the future.
Assumptions | We define an an assumption as information used to establish programme plans or scope that we assumed to be true but may not be true.
Issue | We define an Issue as anything that is unplanned, affecting the programme / project, and that requires an action to resolve and move forward.
Dependency | We define a dependency as a milestone that must occur before another area can progress.
| Impact | [5 empty] | **The MPO will only focus on high Impact risks and issues
Critical Milestones
| Not at Risk |  | The Milestone is ON track and being managed by the Major Programme and is likely to meet its agreed baseline date.
| At Risk |  | The Milestone is OFF track and is unlikely to meet the agreed baseline date, mitigation actions will need to be taken.
Dependencies
| Not at Risk |  | The Dependency is ON track and being managed by the Major Programme and is likely to meet its agreed baseline date.
| At Risk |  | The Dependency is OFF track and is unlikely to meet the agreed baseline date, mitigation actions will need to be taken.
Workstreams | Escalate | Status | Risk mitigation strategy | Priority | Agreement status | RAG
Board rounds and criteria-led discharge | Yes | Open | Avoid |  | Identified | R
Medicines to take out (TTOs) | No | Closed | Reduce | High | Meeting planned | A
Transport and discharge lounge |  | Occurred | Fallback | Medium | Agreed | G
Complex discharges |  |  | Transfer | Low | Delivered
Data and measurement |  |  | Share |  | Delivered late
PMO, comms and engagement |  |  | Accept

## Critical Milestones (hidden)
[8 empty] | Dated |  | Not at Risk
[8 empty] | MP Reviewed |  | At Risk
** to be agreed with the MPs
# | MPO Ref # | Prog | Milestone | Definition | Dated | CP/BC | Baselined | Status | Commentary
1 | [9 empty] | MP Reviewed
2
3
4
6
7
8
9
10
12
13
14
15
16
17
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77

## MP Dependency (hidden)
[10 empty] | Dated |  |  | Not at Risk
[10 empty] | MP Reviewed |  |  | At Risk
** to be agreed with the MPs
# | MPO Ref | Dependency | Definition/Descrption | Impact | Outbound (sending from) | Inbound (Receiving) | Owner | Date Required | Category | RAG Rating | Status | Commentary
1 | [12 empty] | MP Reviewed
2
3
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20