## Slide 1: Discharge Flow Programme Highlight Reports
13 May 2026
V1 October 2022

## Slide 2: TTOs Workstream Highlight Report
Brief | Write TTOs the day before discharge, put pharmacy technicians on the wards and track TTO ready times on all 8 medical wards.
Leads | Arjun Mehta (Pharmacy Technician Lead), Leila Haddad (Lead Pharmacist); CITI support: Hannah Lee
Teams involved | Pharmacy, 8 medical ward teams, junior doctors, Digital (TTO tracker)
Key achievements | TTO ready time down from 4.2 to 2.6 hours. Both pharmacy technicians started on 5 May. 71% of TTOs on Wards 5 and 6 now written the day before. |  | 
Key Metrics | Metric | Target | Current
 | TTO ready time (hours) | 2.0 | 2.6
 | TTOs written the day before | 80% | 71%
 | Discharges before midday | 33% | 24%
Key Decisions | Escalations | Risk and Issues | RAG
D-004: weekend TTO cover to be funded from the technician budget (agreed 28/04) | Junior doctor rota gaps on Wards 1 to 4 stop TTOs being written the day before. Ask: Clinical Director to raise with the rota team | R-003 Technicians pulled to dispensary on busy days (amber). I-002 Tracker ward codes wrong on 2 wards (amber) | A
Key outputs/ deliverables | % done + RAG | Target end date | Progress | Next steps
TTO process for the day before discharge | 100% | 10/04 | Agreed by pharmacy and medical staff; on the intranet | Add to junior doctor induction (August)
2 pharmacy technicians on the wards | 90% | 29/05 | Both started 5 May; rota covers 8 wards weekdays | Agree weekend cover with pharmacy
Daily TTO tracker | 60% | 22/05 | Built; ready times on 5 of 8 wards. Data gaps on Wards 2 and 3 | Fix ward codes with Digital (I-002)
Spread to all 8 wards | 40% | 05/06 | Wards 1 to 4 behind: junior doctor rota gaps | Escalate rota gaps to the leadership meeting
Key | Delayed against plan, escalate
 | Slight delay or at risk of delay
 | On track with plan, no delays likely
 | Complete
Reporting date 13 May 2026
V1 October 2022

## Slide 3: Compliment/Win of the Week
“Mr K went home at 10:15 with his medicines explained, two hours earlier than his last stay. His daughter said it was the calmest discharge we've had.”
Shout out to Arjun and the Ward 6 team
V1 October 2022