## Slide 1
Project summary |  |  | SRO: Dr Amara Okafor, Chief of Medicine
Patients on our medical wards wait most of the day to go home: only 16% leave before midday, so A&E patients wait for beds into the evening. We will redesign the discharge day with ward teams, pharmacy and transport so patients who are ready go home in the morning. In place: this scope, SRO sign-off (5 Jan), CITI support plan (in draft). To follow: PID, resource plan, comms plan. |  |  | Key contact: James Holloway, Senior Improvement Manager, CITI
 |  |  | Parent programme: Urgent and Emergency Care Programme
Scope |  |  | Parent programme
In scope: discharges from the 8 adult medical wards (Wards 1 to 8), Monday to Friday first, then weekends; board rounds, TTOs, transport bookings, the discharge lounge and complex discharges with our local authority partners. Out of scope: surgical and paediatric wards, the Emergency Department, community bed capacity and changes to the patient transport contract. |  |  | 
Benefits | Delivery & resourcing | Budget | Stakeholders
Fewer A&E patients waiting for a bed in the afternoon and evening. About 3,000 bed days a year released (about £1.2m of cost avoided). Patients home earlier in the day, with their medicines. Supports the Trust strategy for urgent care. | SRO Dr Amara Okafor; Programme Manager James Holloway with 4 CITI improvement staff. Ward time: each ward manager 2 hours a week, consultant leads 1 session a fortnight. Resource plan to follow. | £35k capital for lounge chairs and refurbishment (agreed). £95k a year for 2 pharmacy technicians, to be agreed through the business case in March. CITI time from the existing CITI budget. | Stakeholder map drafted: ward teams, pharmacy, patient transport, the discharge team, local authority social work, patients and carers, and the Urgent and Emergency Care Programme Board.
Governance | Assumptions | Risks & issues | Constraints & dependencies
Fortnightly Programme Leadership Meeting chaired by the SRO, reporting monthly to the Medicine Clinical Group Executive Committee and the UEC Programme Board. Escalations go to the SRO. | Ward teams can free 2 hours a week for the work. Pharmacy technician posts are approved by March. The transport provider can take morning bookings at no extra cost. | Risk: winter pressures pull ward staff away from the work. Risk: the business case for pharmacy technicians is delayed. Issue: no reliable data yet on TTO ready times. | Constraint: the discharge lounge has 12 chairs and 2 beds. Dependent on the Digital team for an EDD field in the board round view, and on the local authority for daily social work input.
Medicine Clinical Group
Acute and General Medicine
Completed 12 January 2026
V1 October 2022
High Level Scoping Document