V1 October 2022

Discharge Flow Programme

Project Initiation Documentation

Date: 26/01/26, Version: 1.0

# Contents

1	Introduction	1

1.1	Case for change	2

1.2	Objectives	2

2	Project approach	2

2.1	Principles	3

2.2	Resourcing	3

2.2.1	Team	3

2.2.2	Funding	3

2.2.3	Other corporate support (e.g. Essentia, Digital)	3

2.3	Timescales	3

3	Programme management	3

3.1	Leadership	4

3.2	Governance	4

3.3	Key Risks and Issues	4

3.4	Key interdependencies	4

3.5	Key stakeholders	4

4	Benefits	4

4.1	Return on investment	5

4.2	Key Performance Indicators	5

4.3	Other planned benefits (e.g. quality, experience)	5

# Introduction

## Case for change

Only 16% of patients on our 8 adult medical wards go home before midday, against 33% in the best-performing trusts. Beds free up late in the day, so patients in A&E wait for a bed into the evening: in December 2025, 41% of medical admissions waited more than 4 hours in A&E after the decision to admit.

Average length of stay on the 8 wards is 7.4 days. A November 2025 audit of 120 discharges found medicines to take out (TTOs) ready on average 4.2 hours after they were prescribed, and 1 in 3 patients waiting on the ward for transport after they were ready to go.

Patients tell us the day they go home is long and uncertain: 'I was told I could go at 9 and left at 6.'

## Objectives

1. Increase discharges before midday on the 8 medical wards from 16% to 33% by 30 September 2026.

2. Reduce average length of stay from 7.4 to 6.9 days by 30 September 2026, releasing about 3,000 bed days a year.

3. Reduce the time from TTO prescribed to ready from 4.2 to 2 hours by 31 July 2026.

4. Set an expected discharge date within 24 hours of admission for 90% of patients by 30 September 2026.

5. Do this without a rise in readmissions within 30 days (13.8%).

# Project approach

## Principles

We will redesign the discharge day with the people who do the work, using Plan, Do, Study, Act cycles. We will start on Wards 5 and 6 in March and spread ward by ward, so all 8 wards are live by June.

Four core workstreams (board rounds and criteria-led discharge; TTOs; transport and the discharge lounge; complex discharges) are supported by two enabling workstreams (data and measurement; PMO, comms and engagement).

Progress is measured weekly on SPC charts and reported through highlight reports and a fortnightly leadership report. The programme closes at the end of September 2026, when the work is handed to the Clinical Group.

## Resourcing

The programme needs CITI improvement support and protected time from the Clinical Group, as set out below and in the resource planner.

### Team

CITI: Programme Director (0.2 WTE), Programme Manager (1.0 WTE), 3 Improvement Managers and a Project Manager (2.8 WTE in total), Senior Analyst (0.4 WTE), PMO Officer (0.5 WTE).

Clinical Group: SRO and Accountable Executive (0.1 WTE each), clinical lead (1 session a week), matron (0.2 WTE), ward managers (2 hours a week each), lead pharmacist (0.2 WTE).

### Funding

£35k capital for discharge lounge chairs and refurbishment (agreed). £95k a year revenue for 2 pharmacy technicians (business case to the March investment panel). CITI time is met from the CITI budget.

### Other corporate support (e.g. Essentia, Digital)

Digital: an expected discharge date field in the board round view. Estates: lounge refurbishment. Communications: launch, patient leaflet and case study. Procurement: patient transport contract.

## Timescales

The programme runs from mobilisation in February 2026 to closure on 30 September 2026. The key milestones are:

| ID | Milestone | Date |
| --- | --- | --- |
| M1 | Kick-off and mobilisation workshop | 02/02/2026 |
| M2 | Baseline agreed | 23/02/2026 |
| M3 | Board round tested on Wards 5 and 6 | 27/03/2026 |
| M4 | Pharmacy technicians in post | 05/05/2026 |
| M5 | All 8 wards live | 05/06/2026 |
| M6 | Handover to the Clinical Group | 31/08/2026 |
| M7 | Closure report | 30/09/2026 |

# Programme management

## Leadership

The programme is led by:

SRO: Dr Amara Okafor, Chief of Medicine

Project Manager: James Holloway, Senior Improvement Manager, CITI

Clinical Lead: Dr Sofia Marquez, Consultant Physician

Operational Lead: Grace Mensah, General Manager, Acute Medicine

## Governance

A fortnightly Programme Leadership Meeting, chaired by the SRO, oversees progress, risks, resources and benefits. A weekly programme huddle, chaired by the Programme Manager, reviews highlight reports from each workstream. The programme reports monthly to the Medicine Clinical Group Executive Committee and the Urgent and Emergency Care Programme Board.

Accountable Forum: Medicine Clinical Group Executive Committee

## Key Risks and Issues

The key risks and issues at the start of the programme are below. The full list is in the RAID log.

| Risk/ Issue Description | Planned Mitigation |
| --- | --- |
| Risk: winter-level bed pressures pull ward staff away from training and testing. | Start with 2 wards; 30-minute training slots at ward huddles; matrons protect time. |
| Risk: the pharmacy technician business case is delayed. | Take to the March investment panel; interim bank cover agreed. |
| Risk: changes are not kept up after support ends, as happened after the 2024 pilot. | Ward champions, quarterly Flow Manual audit and a planned handover from July. |
| Issue: no reliable data on TTO ready times. | Senior Analyst to build a TTO tracker from the pharmacy system by end of February. |

## Key interdependencies

The programme depends on:

| Dependency Description | Linked Projects/ Programmmes |
| --- | --- |
| An expected discharge date field in the board round view | Digital: electronic patient record team |
| Named social workers for the daily transfer of care huddle | Local authority hospital social work team |
| Same day emergency care changes, so medical admissions don't rise | Urgent and Emergency Care Programme |

## Key stakeholders

The key stakeholders are below. The stakeholder map and communication plan has the full list.

| Name | Title | Project Role |
| --- | --- | --- |
| Dr Amara Okafor | Chief of Medicine | SRO |
| Tom Reid | Director of Operations, Medicine | Accountable Executive |
| Priya Nair | Head of Transformation, CITI | Programme Director |
| Leila Haddad | Lead Pharmacist, Medicine | TTO workstream clinical lead |
| Martin Doyle | Hospital Social Work Manager, local authority | Partner, complex discharges |
| Mark Ellis | Contract Manager, patient transport provider | Senior supplier |

# Benefits

## Return on investment

Return is cost avoided from about 3,000 bed days a year at £400 a bed day, from half way through year 1. Figures in £ thousands.

|  |  | Y1 | Y2 | Y3 | Y4 | Y5 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Capital | Investment | 35 | 0 | 0 | 0 | 0 | 35 |
|  | Return | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Net Benefit | -35 | 0 | 0 | 0 | 0 | -35 |
| Revenue | Investment | 180 | 95 | 95 | 95 | 95 | 560 |
|  | Return | 600 | 1,200 | 1,200 | 1,200 | 1,200 | 5,400 |
|  | Net Benefit | 420 | 1,105 | 1,105 | 1,105 | 1,105 | 4,840 |

## Key Performance Indicators

We will track these weekly on SPC charts. Readmissions is a balancing measure.

| Indicator | Baseline | Target | Target Date |
| --- | --- | --- | --- |
| Discharges before midday (8 wards) | 16% | 33% | 30/09/2026 |
| Average length of stay (days) | 7.4 | 6.9 | 30/09/2026 |
| TTO ready time, prescribed to ready (hours) | 4.2 | 2.0 | 30/09/2026 |
| Eligible discharges through the lounge | 12% | 40% | 30/09/2026 |
| Expected discharge date set within 24 hours | 41% | 90% | 30/09/2026 |
| Readmissions within 30 days (balancing) | 13.8% | No rise | 30/09/2026 |

## Other planned benefits (e.g. quality, experience)

Patients: home earlier in the day, with their medicines explained and a clear time to leave.

A&E: shorter waits for a medical bed in the afternoon and evening.

Staff: calmer afternoons, fewer late discharges and less time chasing transport and TTOs.

Quality: a standard board round on every medical ward, built into induction and the Flow Manual audit.