## Sheet1
Resource Planner & Tracker | [7 empty] | V1 October 2022
Project: | Discharge Flow Programme
Project Manager: | James Holloway
Project Start Date: | 2026-02-02
| Resource Name | Resource Role | Total Planned Days
Planned Days | James Holloway | Programme Manager |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3
| Ben Carter | Improvement Manager |  |  |  | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3
| Hannah Lee | Improvement Manager |  |  |  | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1
| Chloe Evans | Project Manager |  |  |  | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1
| Sam Patel | Improvement Manager |  |  |  | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1
| Omar Siddiqui | Senior Analyst |  |  |  | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1
Predicted time (in days) required for each resource
| Resource Name | Resource Role | Total Planned Days | Actual Days Worked | Days Remaining
Burn Rate | [5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
[6 empty] | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5
[6 empty] | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
[6 empty] | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3
[6 empty] | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3
[6 empty] | 1 | 1 | 3 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Actual resource usage (in days) - requires updating regularly
| Resource Name | Resource Role | Total Planned Days | Actual Days Worked | Days Remaining
External Resources
Any additional resources from an external source (consultancy etc)
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Grundy Sam (SGRUNDY) Hi Sam, are we able to have a comment in here to describe what 'planned days' means?
Note on A19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: as above @Grundy Sam (SGRUNDY)
Note on A30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Grundy Sam (SGRUNDY) as above

## Visual
Name | Time