## Slide 1: Key programme roles
V1 October 2022
Key Programme Roles
Role | Name | High Level Description | Comments
SRO | Dr Amara Okafor | Sets the overall direction of for the programme Focus is ‘up and out’ to the senior internal (and external) stakeholders Owns the business case and programme requirements | Chairs the leadership meeting; owns the case for change and the benefits
Accountable Executive | Tom Reid | Leads development of the business case on behalf of SRO Chairs the senior leadership programme meetings and other programme wide meetings Accountable for overall delivery of the programme and constituent workstreams | Chairs escalations with ward leaders; signs off the business case
Programme Director(s) | Priya Nair | Fulfils the Accountable Executive role at the programme level Leads the most challenging and complex programmes Primary responsibility for successful delivery of required outcomes Builds and manages the programme team, ensuring programme is appropriately resourced Manages key suppliers and other critical stakeholders | Leads CITI support, 0.2 WTE
Programme Manager | James Holloway | Responsible for the day-to-day delivery of the programme, supporting the Programme Director and SRO Drafts the programme business case with input from project managers and SMEs Manages the programme plan and key dependencies between projects and workstreams | Full time; runs the plan, RAID log and reporting
Clinical, Operational and Nursing Leads | Dr Sofia Marquez, Grace Mensah, Daniel Cho | Senior Manager drawn from the business areas impacted by the programme. Acts as a bridge into, and ‘Change Champion’ for, their respective area Focus is benefits definition, realisation and ensuring changes become BAU | One lead per workstream (see organisation chart)
PMO Support | Ruth Adeyemi | Runs the document repository (Teams site) on behalf of Programme Manager/Director; maintains the ‘drum-beat’ of meetings and reporting; identifies and disseminates best practice Responsible for delivery of Programme Controls and Information Management to selected projects and programmes Will offer guidance and provide assurance on the delivery of controls to the team | Owns the Teams site, action log and meeting drum-beat
Programme Assurance | Kate Burrows | Supports definition of Assurance Plan for each Project/Programme and undertakes independent reviews as required | Gateway review at end of mobilisation (Feb) and before closure (Sep)
CITI Support (Delivery, Change, Improvement Managers and Analysts) | Ben Carter, Hannah Lee, Chloe Evans, Sam Patel, Omar Siddiqui | Responsible for day-to-day delivery of constituent workstreams on behalf of the Programme Manager Tracks success of delivery to agreed schedule, cost and quality parameters | Each supports one workstream; Omar supports data
Engagement Director / Senior Supplier | Mark Ellis | Member of the programme , accountable for the quality of supplier’s products Has authority to commit or acquire supplier resources required for delivery | Agrees morning transport capacity; attends transport group