## Slide 1: Stakeholder Map/Mapping Tool
Stakeholder interest in work or service | Supporters show consideration Interested but less influential stakeholders may be a distraction. Keep informed and involved in their interest areas. Manage and acknowledge Our stakeholders: Patients and carers, Ward housekeepers, Patient panel | Champions manage closely Highly interested and highly influential stakeholders should be involved in the work or in the running of the service. Consult and engage regularly & involve in decision making Manage most thoroughly Our stakeholders: Ward managers and matrons, Pharmacy team, Consultant physicians, Discharge team
 | Sleepers minimal effort Neither influential nor interested, keep informed and monitor regularly in case of changes in their status but should not be distracted from the work Regular, minimal contact Our stakeholders: Estates (lounge refurbishment), Volunteers service | Blockers keep satisfied Focus on engaging, listening to and influencing. Should be communicated with and managed to try and increase their interest. Anticipate and meet needs Our stakeholders: Patient transport provider, Local authority social work, Clinical Group Executive Committee
 | Stakeholder ability to influence work or service | 
V1 October 2022

## Slide 2: Stakeholder communication planning tool
Stakeholder​ | Power / interest​ | Key interest / Issues​ | Communication Vehicle​ | Frequency​ | Format | Content Provided
Ward managers and nurses (8 wards) | High / High | Time to take part; staffing on busy days | Ward huddle, workstream group | Daily / weekly | Face to face | Ward measures, PDSA plans, wins
Consultants and junior doctors | High / Medium | Board round time; writing TTOs the day before | Medical staff meeting, Teams post | Monthly | Slides, 5-minute slot | Board round standard, criteria-led discharge
Pharmacy team | High / High | Workload; technician posts | Pharmacy team meeting | Fortnightly | Face to face | TTO ready times, rota changes
Patient transport provider | Medium / Low | Contract terms; vehicle capacity | Contract meeting | Monthly | Meeting, email | Booking times and volumes
Local authority social work | High / Medium | Staff time for the daily huddle | Transfer of care meeting | Twice weekly | Teams call | Complex discharge list, delays
Patients and carers | Low / High | Knowing when they will go home | Leaflet, ward posters, patient panel | Ongoing; panel quarterly | Print, face to face | What to expect on the day you go home
Clinical Group Executive Committee | High / Medium | Bed pressures; money | Leadership report | Monthly | Report | Progress, risks, decisions needed
Project Name: Discharge Flow Programme | Start date: 12 January 2026 | Completion date: 30 September 2026 | Project manager: James Holloway
V1 October 2022