## Summary (hidden)
Major Programmes Risks, Actions, Issues, Dependencies and Opportunities (RAIDO)
This document supports the MP Integrated Overview plan. To document the key risks, milestones and dependencies that have been identified.
What is the document used for?
This document is managed in conjunction with the Major Programmes to document the delivery status and to identify key issues that need to go to the attention of the TMP E and B.
Who manages this document?
The document is managed and owned by the MPO Business Partners, with each Business Partner being responsible for updating information related to their programme.
MPO Business Partners Alignment
a. Kathryn Ascroft - Evelina, RBH-KHP Partnership Programme and Merger Integration Programme, Trust Operating Model
b. Lucy Oliver - Pathology and Apollo
Dated: 10th March 2021
Version: DRAFT_0.1
Major Programmes
Risks, Issues, Dependency's, Milestones and Business Change
(Programme Documents)
Major Programmes Office
High Impact Risks, Issues, and Critical Dependencies and Milestones and Significant Change.
(MPO RAIDO)
Managed through the BP Fortnightly 1:1 Sessions
TMP
Escalations for consideration
(TMP Reports)
Rules/Principles for inclusion into the MPO RAIDO
1. High Impact Major Programme Risks and Issues (Risks scoring 12 and over post mitigation)
2. High Impact Risk and Issues that would have wider trust impact
3. Major Programme Critical Milestones
4. Significant Release of Change into the Trust
5. Dependencies that directly impact the delivery of a critical milestone or a important release of change

## Cover
V1 October 2022
Project:
Project Manager:
RISKS, ASSUMPTIONS, ISSUES AND
DEPENDENCIES (RAID) LOG

## Risks
RISKS
Date of last review
[8 empty] | Pre Mitigation Impact Assessment |  |  |  | Post Mitigation Impact Assessment
| Ref # | Date Raised | Owner | Responsible | Workstream | Title | Description | Likelihood (1-5) | Impact (1-5) | Exposure (L*I) | Mitigation Actions | Likelihood (1-5) | Impact (1-5) | Exposure (L*I) | Trend | Impact Date | Status | Status - commentary | Date closed | Escalate to Exec
| R-001 | [6 empty] | 4 | 2 | 8 |  |  |  | 0
| R-002 | [8 empty] | 0 |  |  |  | 0
| R-003 | [8 empty] | 0 |  |  |  | 0
| R-004 | [8 empty] | 0 |  |  |  | 0
| R-005 | [8 empty] | 0 |  |  |  | 0
| R-006 | [8 empty] | 0 |  |  |  | 0
| R-007 | [8 empty] | 0 |  |  |  | 0
| R-008 | [8 empty] | 0 |  |  |  | 0
| R-009 | [8 empty] | 0 |  |  |  | 0
| R-010 | [12 empty] | 0
| R-011 | [8 empty] | 0
| R-012 | [8 empty] | 0 |  |  |  | 0
| R-013 | [8 empty] | 0 |  |  |  | 0
| R-014 | [8 empty] | 0 |  |  |  | 0
| R-015 | [6 empty] | 4 | 5 | 20 |  |  |  | 0
| R-016 | [8 empty] | 0 |  |  |  | 0
| R-017 | [8 empty] | 0 |  |  |  | 0
| R-018 | [8 empty] | 0 |  |  |  | 0
| R-019 | [8 empty] | 0 |  |  |  | 0
| R-020 | [8 empty] | 0 |  |  |  | 0
| R-021 | [8 empty] | 0 |  | 2 | 3 | 6
| R-022 | [8 empty] | 0 |  |  |  | 0
| R-023 | [8 empty] | 0 |  |  |  | 0
| R-024 | [8 empty] | 0 |  |  |  | 0
| R-025 | [8 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
[10 empty] | 0 |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0

## Issues
ISSUES
Date of last review
| Ref # | Date Raised | Owner | Responsible | Workstream | Title | Description | Impact (1-5) | Actions to resolve | Trend | Status | Status - commentary | Date closed | Escalate to Exec
I-001
I-002
I-003
I-004
I-005
I-006
I-007
I-008
I-009
I-010
I-011
I-012
I-013
I-014
I-015
I-016
I-017
I-018
I-019
I-020
I-021
I-022
I-023
I-024
I-025

## Assumptions
ASSUMPTIONS
Date of last review
| Ref # | Date Raised | Forum raised by | Assumption Title | Assumption Description | Impact of Assumption | Workstream | Owner | Priority | Status
| AS-001 | 2022-06-21
AS-002
AS-003
AS-004
AS-005
AS-006
AS-007
AS-008
AS-009
AS-010
AS-011
AS-012
AS-013
AS-014
AS-015
AS-016
AS-017
AS-018
AS-019
AS-020
AS-021
AS-022
AS-023
AS-024
AS-025

## Dependencies
DEPENDENCIES
Date of last review
| Ref # | Date Raised | Workstream affected | Who is dependent on Delivery? | Who is Responsible for Delivery? | Summary Description | Delivery date | Status | Status commentary | RAG | Priority
DEP-001
DEP-002
DEP-003
DEP-004
DEP-005
DEP-006
DEP-007
DEP-008
DEP-009
DEP-010
DEP-011
DEP-012
DEP-013
DEP-014
DEP-015
DEP-016
DEP-017
DEP-018
DEP-019
DEP-020
DEP-021
DEP-022
DEP-023
DEP-024
DEP-025
Note on F6: This should be the name of the person who the delivering party should reach agreement with

## Definitions and Validation
Definitions
The RAID Log contains four different Logs that include Risks, Assumptions, Issues and Dependencies.
Each log is oriented to have a clear description of each item in them taking into account the following definitions:
Risk | We define a risk as a potential situation that could impact the programme (positively or negatively) in the future.
Assumptions | We define an an assumption as information used to establish programme plans or scope that we assumed to be true but may not be true.
Issue | We define an Issue as anything that is unplanned, affecting the programme / project, and that requires an action to resolve and move forward.
Dependency | We define a dependency as a milestone that must occur before another area can progress.
| Impact | [5 empty] | **The MPO will only focus on high Impact risks and issues
Critical Milestones
| Not at Risk |  | The Milestone is ON track and being managed by the Major Programme and is likely to meet its agreed baseline date.
| At Risk |  | The Milestone is OFF track and is unlikely to meet the agreed baseline date, mitigation actions will need to be taken.
Dependencies
| Not at Risk |  | The Dependency is ON track and being managed by the Major Programme and is likely to meet its agreed baseline date.
| At Risk |  | The Dependency is OFF track and is unlikely to meet the agreed baseline date, mitigation actions will need to be taken.
Workstreams | Escalate | Status | Risk mitigation strategy | Priority | Agreement status | RAG
PMO | Yes | Open | Avoid |  | Identified | R
Comms & Engagement | No | Closed | Reduce | High | Meeting planned | A
POAC |  | Occurred | Fallback | Medium | Agreed | G
Scheduling processes |  |  | Transfer | Low | Delivered
Theatre productivity |  |  | Share |  | Delivered late
Overarching programme |  |  | Accept
Data

## Critical Milestones (hidden)
[8 empty] | Dated |  | Not at Risk
[8 empty] | MP Reviewed |  | At Risk
** to be agreed with the MPs
# | MPO Ref # | Prog | Milestone | Definition | Dated | CP/BC | Baselined | Status | Commentary
1 | [9 empty] | MP Reviewed
2
3
4
6
7
8
9
10
12
13
14
15
16
17
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77

## MP Dependency (hidden)
[10 empty] | Dated |  |  | Not at Risk
[10 empty] | MP Reviewed |  |  | At Risk
** to be agreed with the MPs
# | MPO Ref | Dependency | Definition/Descrption | Impact | Outbound (sending from) | Inbound (Receiving) | Owner | Date Required | Category | RAG Rating | Status | Commentary
1 | [12 empty] | MP Reviewed
2
3
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20