## Sheet1
Resource Planner & Tracker | [7 empty] | V1 October 2022
Project:
Project Manager:
Project Start Date: | 2022-07-01
| Resource Name | Resource Role | Total Planned Days |  |  | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12
Planned Days | Bill | Project Manager | 60 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Ben | Clinical Lead | 11 | bar: 2022-07-04 to 2022-09-12
| Sam |  | 15 |  |  | 2022-06-27: 5; 2022-07-04: 5; 2022-07-11: 5
| Rebecca |  | 20 |  |  | 2022-06-27: 5; 2022-07-04: 5; 2022-07-11: 5; 2022-07-18: 5
0
0
106
Predicted time (in days) required for each resource
| Resource Name | Resource Role | Total Planned Days | Actual Days Worked | Days Remaining | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12
Burn Rate | Bill | Project Manager | 60 | 8 | 52 | 2022-06-27: 3; 2022-07-04: 5
| Ben | Clinical Lead | 11 | 5 | 6 | 2022-06-27: 0; 2022-07-04: 5
| Sam | 0 | 15 | 0 | 15
| Rebecca | 0 | 20 | 0 | 20
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
|  |  | 106 | 0 | 106
Actual resource usage (in days) - requires updating regularly
| Resource Name | Resource Role | Total Planned Days | Actual Days Worked | Days Remaining | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12
External Resources |  |  |  |  | 0
0
| Sam | 0 | 15 | 0 | 15
| Rebecca | 0 | 20 | 0 | 20
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0
Any additional resources from an external source (consultancy etc)
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Grundy Sam (SGRUNDY) Hi Sam, are we able to have a comment in here to describe what 'planned days' means?
Note on A19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: as above @Grundy Sam (SGRUNDY)
Note on A30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Grundy Sam (SGRUNDY) as above

## Visual
Name | Time
Bill | 60
Ben | 11
Sam | 15
Rebecca | 20