## Slide 1: Discharge Flow Programme Leadership Report
14 May 2026

## Slide 2: Discharge Flow Programme Update
Key risks/issues |  | Key risks/issues
R/I# | RAG | Risk/Issue
R-001 |  | Winter-level bed pressures continue into May, so ward staff miss board round training
R-003 |  | Technicians pulled to dispensary on busy days
I-001 |  | Junior doctor rota gaps on Wards 1 to 4: decision needed on locum cover
Wins of the week
Ward 6 reached 38% of discharges before midday for 3 weeks running Both pharmacy technicians started on 5 May
Key Metrics/KPIs
Discharges before midday (8 wards): 24% (baseline 16%, target 33%) Average length of stay (days): 7.1 (baseline 7.4, target 6.9) TTO ready time, prescribed to ready (hours): 2.6 (baseline 4.2, target 2.0) Eligible discharges through the lounge: 31% (baseline 12%, target 40%) Expected discharge date set within 24 hours: 78% (baseline 41%, target 90%)
Reporting date: 14 May 2026
Workstream + RAG | High-level deliverable/Output | % done | Due date | RAG justification | Next steps
Board rounds & CLD | Morning board round live on 6 of 8 wards | 75% | 05/06 | On track; Wards 1 and 2 start 18 May | Train Ward 1 and 2 teams
 | Criteria-led discharge policy | 100% | 24/04 | Approved by Clinical Governance on 24 April | Audit use in June
 | EDD set within 24 hours | 70% | 30/06 | 78% of patients, up from 41% | Add EDD field to board round view (DEP-001)
TTOs & pharmacy | Technicians and TTO the day before | 75% | 05/06 | Wards 1 to 4 behind: junior doctor rota gaps | Escalation: see risks
 | TTO tracker on all wards | 60% | 22/05 | Data gaps on 2 wards | Fix ward codes with Digital
Transport, lounge & complex discharges | Lounge open from 8am | 100% | 30/04 | Lounge use up from 12% to 31% | Promote at ward huddles
 | Daily transfer of care huddle | 80% | 29/05 | Running daily with social work | Start discharge to assess pilot
Key | Delayed against plan, escalate
 | Slight delay or at risk of delay
 | On track with plan, no delays likely
 | Complete