## 1. Cover
Discharge Flow Programme
ACTIONS & DECISIONS LOG
Document contents
Worksheet name | Description
1 Cover | This page
2 Action log | Worksheet where actions should be logged and tracked
3 Decisions log | Worksheet where decisions or decisions to be made should be logged
Lists | Contains lists used to populate drop down boxes

## 2. Action Log
Unique ID | Workstream | Action Description | Forum Raised / Raised by | Date Raised | Owner | Original due date | Revised due date | Status | Commentary | Date Closed
A-001 | PMO, comms and engagement | Set up the Teams site, action log and RAID log | Kick-off, 02/02 | 2026-02-02 | Ruth Adeyemi | 2026-02-06 |  | Closed | Done | 2026-02-05
A-002 | Data and measurement | Build the baseline: discharges before midday by ward, Oct to Dec 2025 | Kick-off, 02/02 | 2026-02-02 | Omar Siddiqui | 2026-02-20 |  | Closed | 16% baseline agreed at leadership meeting | 2026-02-23
A-003 | Medicines to take out (TTOs) | Write the pharmacy technician business case | Leadership meeting, 09/02 | 2026-02-09 | Leila Haddad | 2026-03-06 |  | Closed | Approved 18/03 | 2026-03-18
A-004 | Board rounds and criteria-led discharge | Agree the board round standard with Ward 5 and 6 teams | Board rounds group, 17/02 | 2026-02-17 | Dr Sofia Marquez | 2026-03-13 | 2026-03-27 | Closed | Moved 2 weeks for ward manager leave | 2026-03-25
A-005 | Transport and discharge lounge | Ask the provider for 4 more morning slots a day | Transport group, 02/03 | 2026-03-02 | Kwame Asante | 2026-03-31 |  | Closed | Agreed from 13/04 | 2026-04-09
A-006 | Complex discharges | Agree terms of reference for the daily transfer of care huddle | Transport group, 02/03 | 2026-03-02 | Fiona Gallagher | 2026-04-03 |  | Closed | Signed off with local authority | 2026-04-01
A-007 | Board rounds and criteria-led discharge | Train Ward 1 and 2 teams in the board round standard | Weekly huddle, 11/05 | 2026-05-11 | Joy Adebayo | 2026-05-22 |  | In progress | Ward 1 done; Ward 2 booked 20/05
A-008 | Data and measurement | Fix ward codes for Wards 2 and 3 in the TTO tracker (I-002) | Weekly huddle, 27/04 | 2026-04-27 | Omar Siddiqui | 2026-05-08 | 2026-05-22 | In progress | Waiting on Digital
A-009 | Medicines to take out (TTOs) | Agree weekend technician cover with the pharmacy manager | TTO group, 07/05 | 2026-05-07 | Leila Haddad | 2026-05-29 |  | Open
A-010 | PMO, comms and engagement | Write the patient leaflet with the patient panel | Leadership meeting, 30/04 | 2026-04-30 | Nadia Rahman | 2026-06-12 |  | Open | Panel meets 03/06
A-013
A-014
A-015
A-017
A-018
A-029
A-019
A-020
A-021
A-022
A-023
A-024
A-025
A-026
A-027
A-028
A-029
A-030
A-031
A-032
A-033
A-034
A-035
A-036
A-037
A-038
A-039
A-040
A-041
A-042
A-043
A-044
A-045
A-046
A-047
A-048
A-049
A-050
A-051
A-052
A-053
A-054
A-055
A-056
A-057
A-058
A-059
A-060
A-061
A-062
A-063
A-064
A-065
A-066
A-067
A-068
A-069
A-070
A-071
A-072
A-073
A-074
A-075
A-076
A-077
A-078
A-079
A-080
A-081
A-082
A-083
A-084
A-085
A-086
A-087
A-088
A-089
A-090
A-091
A-092
A-093
A-094
A-095
A-096
A-097
A-098
A-099
A-100
A-101
A-102
A-103
A-104
A-105
A-106
A-107
A-108
A-109
A-110
A-111
A-112
A-113
A-114
A-115
A-116
A-117
A-118
A-119
A-120
A-121
A-122
A-123
A-124
A-125
A-126
A-127
A-128
A-129
A-130
A-131
A-132
A-133
A-134
A-135
A-136
A-137
A-138
A-139
A-140
A-141
A-142
A-143
A-144
A-145
A-146
A-147
A-148
A-149
A-150
A-151
A-152
A-153
A-154
A-155
A-156
A-157
A-158
A-159
A-160
A-161
A-162
A-163
A-164
A-165
A-166
A-167
A-168
A-169
A-170
A-171
A-172
A-173
A-174
A-175
A-176
A-177
A-178
A-179
A-180
A-181
A-182
A-183
A-184

## 3. Decisions Log
DECISIONS LOG Discharge Flow Programme
Unique ID | Workstream | Date raised | Priority | Decision to be made | Decision due date | Final decision | Approval by (person or forum) | Decision date | Status | Commentary | Reference materials
D-001 | Board rounds and criteria-led discharge | 2026-02-09 | High | Which wards test the board round first? | 2026-02-23 | Wards 5 and 6: keen ward managers, and Ward 6 ran the 2024 pilot | Programme Leadership Meeting | 2026-02-23 | Closed |  | Baseline by ward
D-002 | Data and measurement | 2026-02-09 | High | Which measure is the main outcome? | 2026-02-23 | Discharges before midday, with length of stay and readmissions alongside | Programme Leadership Meeting | 2026-02-23 | Closed |  | Benefits register
D-003 | Transport and discharge lounge | 2026-03-02 | Medium | Should the lounge open at 8am, and who staffs it? | 2026-03-30 | Open at 8am from 30/04, staffed by moving 1 healthcare assistant from the late shift | Medicine senior leadership team | 2026-03-26 | Closed |  | Lounge activity data
D-004 | Medicines to take out (TTOs) | 2026-04-14 | Medium | How do we fund weekend TTO cover? | 2026-04-28 | From the technician budget, by staggering rotas | Programme Leadership Meeting | 2026-04-28 | Closed |  | Rota options paper
D-005 | Medicines to take out (TTOs) | 2026-05-14 | Very high | Locum cover for junior doctor rota gaps on Wards 1 to 4 (I-001)? | 2026-05-28 |  | Medicine Clinical Group Executive Committee |  | Open | Escalated from leadership meeting 14/05 | Rota gap analysis
D-006
D-007
D-008
D-009
D-010
D-011
D-012
D-013
D-014
D-015
D-016
D-017
D-018
D-019
D-020
D-021
D-022
D-023
D-024
D-025
D-026
D-027
D-028
D-029
D-030
D-031
D-032
D-033
D-034
D-035
D-036
D-037
D-038
D-039
D-040
D-041
D-042
D-043
D-044
D-045
D-046
D-047
D-048
D-049
D-050
D-051
D-052
D-053
D-054
D-055
D-056
D-057
D-058
D-059
D-060
D-061
D-062
D-063
D-064
D-065
D-066
D-067
D-068
D-069
D-070
D-071
D-072
D-073
D-074
D-075
D-076
D-077
D-078
D-079
D-080
D-081
D-082
D-083
D-084
D-085
D-086
D-087
D-088
D-089
D-090
D-091
D-092
D-093
D-094
D-095
D-096

## Lists
Workstreams | Priority | Status
Board rounds and criteria-led discharge | Very high | Open
Medicines to take out (TTOs) | High | Closed
Transport and discharge lounge | Medium | In progress
Complex discharges | Low | On hold
Data and measurement | Very low
PMO, comms and engagement