## Slide 1: Discharge Flow Programme: Support Plan
January 2026
V1 October 2022

## Slide 2: Context and background
Context:
Only 16% of patients on our 8 medical wards go home before midday, against 33% in the best-performing trusts. Beds free up late, so A&E patients wait for a bed into the evening and the wards start each day full.
Average length of stay is 7.4 days. A discharge audit in November 2025 found TTOs ready on average 4.2 hours after prescribing, and 1 in 3 patients waiting on the ward for transport.
A 2024 pilot of criteria-led discharge on Ward 6 raised morning discharges to 27% but was not kept up after the pilot ended.
Request for support:
6 months of CITI improvement support (March to August 2026), after a mobilisation month in February, to redesign the discharge day on all 8 wards with ward teams, pharmacy, transport and the discharge team.
Areas affected: the 8 medical wards, pharmacy, the discharge lounge, patient transport bookings and the discharge team.

## Slide 3: Scoping, deliverable and metrics
This table outlines the proposed scope for resources between CITI and the Medicine Clinical Group.
Priority area/ Workstreams | Scope / Activities | Deliverables | Metrics
Board rounds and criteria-led discharge | Standard morning board round on every ward; expected discharge date set within 24 hours; criteria-led discharge for suitable patients. | Board round standard and role cards; criteria-led discharge policy; training for 8 ward teams. | Discharges before midday; EDD set within 24 hours.
Medicines to take out (TTOs) | Write TTOs the day before discharge; pharmacy technicians on wards; track TTO ready times. | TTO process redesign; 2 pharmacy technician posts; daily TTO tracker. | TTO ready time, prescribed to ready.
Transport, lounge and complex discharges | Morning transport bookings; use the discharge lounge from 8am; daily transfer of care huddle. | Transport booking process; lounge operating standard; transfer of care hub huddle. | Lounge use; length of stay; readmissions (balancing).

## Slide 4: Improvement programme approach
Track the measures weekly on SPC charts and collect the blockers ward teams raise
Run structured problem solving on the main blockers (TTO delays, transport, social care)
Share each ward's measures at its daily huddle and in the weekly highlight report
Agree how the changes will be kept up: audits, leader visits and ward champions
Finalise the standard operating procedures, role cards and process documents
Build the standards into induction, ward training and the Flow Manual audit
Evaluate the impact and experience, and agree next steps with the Clinical Group
Recommend how to spread the standards to surgical wards
Test the morning board round and criteria-led discharge on Wards 5 and 6, then spread ward by ward
Write role cards and standard operating procedures for board rounds, TTOs and the lounge
Coach ward teams on the ward, including bite-size training and visual management boards
Work with pharmacy, transport and the discharge team to track the effect on their work
Set up the leadership meeting, workstream groups and ward champions; launch the programme with all 8 wards
Agree the board round and discharge standards with ward teams
Build the baseline dashboard: discharges before midday, length of stay, TTO times, lounge use
Finalise plans and link to the Urgent and Emergency Care Programme and the transfer of care hub
We will work through four Plan, Do, Study, Act stages with the ward teams, starting on Wards 5 and 6 and spreading to all 8 wards.
01
Plan
02
Do
03
Study
04
Act
Mobilise and engage
Agree standards
Baseline metrics & targets
Test on 2 wards
Train & coach
Engage partners
Finalise standards
Embed in training
Evaluate & spread
Track impact weekly
Solve blockers
Sustainability plan
Notes: Not representative of timelines – Plan to be significantly shorter than other parts (with Plan and Do happening concurrently)

## Slide 5: Improvement programme principles
    Driven by the Clinical Group, with support from CITI
Governed and steered by Clinical Group Leadership team, and supported by CITI Improvement team
Agreed metrics to track impact, and established governance to ensure momentum
Involvement of Clinical Group leads in engaging staff and unblocking barriers
Your commitment
Our promise
    Standard solutions, consistent approach but bespoke support
Standardised solutions to be developed with the multi-disciplinary team
Consistent approach but bespoke to each ward, with support tailored to challenges faced by the teams
Empower ward teams with greater understanding of operational performance management (incl. visibility of metrics to ward team leads)
    On-the-ground support with a ‘live redesign’ approach
Pragmatic on-the-ground support, similar to the approach taken in late 2021.
CITI Team to sit with Clinical Group team wherever possible (e.g. base at Becket House)
CITI Team to be present on the wards, providing hands-on support to embed new ways of working
Support with ‘live improvements’ and on-the-ground capability building
The partnership between CITI and the Medicine Clinical Group aims to deliver change collaboratively, as one extended management and improvement team. Our approach will be pragmatic and will need involvement from leaders at all levels of the Clinical Group.
Notes: Discussion point – “your commitment” [outlined governance later in document]

## Slide 6: Proposed governance and operational management
Steering Groups | Programme Leadership Meeting (fortnightly, chair: SRO) | Medicine Clinical Group Executive Committee (monthly)* | UEC Programme Board (monthly)*
Progress and Impact Tracking | Weekly measures dashboard (SPC charts) | Weekly highlight reports from each workstream | Monthly benefits review
Delivery managed by CITI and ward teams | Programme weekly huddle (chair: Programme Manager) Workstream user groups | Daily ward discharge huddles* | Transfer of care meeting (twice weekly)*
The Discharge Flow Programme will use the Clinical Group's existing meetings where possible, so all improvement work is overseen in one place.
* Utilise existing meeting where possible

## Slide 7: Programme management
Risk/ Issue Description | Planned Mitigation
Winter pressures pull ward staff away from the work | Start on 2 wards in March; keep board rounds to 30 minutes; agree protected time with matrons
Pharmacy technician business case delayed | Take the case to the March investment panel; interim bank cover agreed
No reliable data on TTO ready times | Analyst to build a TTO tracker from the pharmacy system by end of February
Changes not kept up after support ends (as in the 2024 pilot) | Ward champions, Flow Manual audit and handover to the Clinical Group from July
SRO: Dr Amara Okafor, Chief of Medicine
Project Manager: James Holloway, Senior Improvement Manager, CITI
Clinical Lead: Dr Sofia Marquez, Consultant Physician
Operational Lead: Grace Mensah, General Manager, Acute Medicine
Dependency Description | Linked projects/programmes
EDD field in the board round view | Digital: electronic patient record team
Daily social work input to the transfer of care huddle | Local authority hospital social work team
Same day emergency care changes | Urgent and Emergency Care Programme
Morning transport capacity | Patient transport contract (Procurement)
Key interdependencies
Key risks and issues

## Slide 8: Benefits and KPI’s
 |  | Y1 | Y2 | Y3 | Y4 | Y5 | Total
Capital | Investment | £35k | £0 | £0 | £0 | £0 | £35k
 | Return | £0 | £0 | £0 | £0 | £0 | £0
 | Net Benefit | -£35k | £0 | £0 | £0 | £0 | -£35k
Revenue | Investment | £180k | £95k | £95k | £95k | £95k | £560k
 | Return | £600k | £1.2m | £1.2m | £1.2m | £1.2m | £5.4m
 | Net Benefit | £420k | £1.1m | £1.1m | £1.1m | £1.1m | £4.8m
Indicator | Baseline | Target | Target Date
Discharges before midday (8 wards) | 16% | 33% | Sep 2026
Average length of stay (days) | 7.4 | 6.9 | Sep 2026
TTO ready time, prescribed to ready (hours) | 4.2 | 2.0 | Sep 2026
Eligible discharges through the lounge | 12% | 40% | Sep 2026
Return on investment
Key performance indicators

## Slide 9: Resource plan
To resource these priority areas, we propose the following WTE from 2 February to 30 September 2026. This will let us support all 8 medical wards. Other initiatives will need further resources.
Priority area | Clinical Group Resource | Improvement/Project Resource
Programme leadership and PMO | SRO 0.1 WTE; Accountable Executive 0.1 WTE | Programme Director 0.2 WTE; Programme Manager 1.0 WTE; PMO 0.5 WTE
Board rounds and criteria-led discharge | Board rounds: clinical lead 1 session a week; matron 0.2 WTE; ward managers 2 hours a week each TTOs: lead pharmacist 0.2 WTE; 2 pharmacy technicians (new posts) | Board rounds: Improvement Manager 1.0 WTE TTOs: Improvement Manager 0.6 WTE
Medicines to take out (TTOs) |  | 
Transport, lounge and complex discharges | Flow manager 0.2 WTE; discharge team lead 0.2 WTE; social work input to the daily huddle | Project Manager 0.6 WTE; Improvement Manager 0.6 WTE
Data and measurement | Information team: data extracts | Senior Analyst 0.4 WTE

## Slide 10: Next Steps
Confirm your approval of this Support Plan, including any amendments, by 23 January
Set up the kick-off meeting (the first in 2 weeks' time, on 2 February)
Identify members of the working group for:
Agree which forums to attend to socialise this work across all members of the multi-disciplinary team:
  Medicine senior leadership team, ward managers' meeting, pharmacy team meeting, transfer of care meeting
Board rounds group Weekly, Tuesday 2pm | Dr Sofia Marquez, Joy Adebayo, 8 ward managers, Ellie Brooks, Ben Carter
TTO group Fortnightly, Thursday 10am | Leila Haddad, Arjun Mehta, 2 junior doctor reps, Hannah Lee
Transport and discharge group Fortnightly, Monday 1pm | Kwame Asante, Fiona Gallagher, Martin Doyle, Mark Ellis, Chloe Evans, Sam Patel