## Slide 1
Governance Chart
Governance
Engages with clinical & operational groups
Trust Executive Committee
Medicine Clinical Group Board
Ward 'Big Room' improvement huddles
Discharge projects run by single wards
Key forums/ meetings:
Targeted work
Operational delivery
Medicine Operational Group
Medicine Clinical Governance
General Managers' Forum
Patient Flow Group
Pharmacy Board
Patient Experience Committee
Local authority discharge partnership
ICB urgent care meeting
Engagement with other forums
Discharge Flow Programme
Medicine senior leadership team (weekly)
Urgent and Emergency Care Programme
Workstreams: Front door, Same day emergency care, Virtual wards, Discharge flow
UEC Programme Board (monthly)
Medicine Clinical Group Executive Committee
Programme Leadership Meeting (fortnightly)
Ward discharge huddles (daily)
Workstream user groups
Transfer of care meeting (twice weekly)
Programme weekly huddle
Weekly huddle
V1 October 2022

## Slide 2
Governance Forums
The below table summarises the purpose and responsibilities for the key programme governance forums
 | Programme Leadership Meeting (fortnightly, 1 hour) | Programme Weekly Huddle (Mondays, 30 minutes) | Workstream User Groups (weekly or fortnightly)
Purpose | Oversees progress against the aim of 33% of discharges before midday. Escalation point for risks and issues; agrees structure, resourcing and budget. | Shares the progress of every workstream (board rounds, TTOs, transport and lounge, complex discharges) against plan, and the links between them. | Gives ward and partner teams a say in each workstream's changes and plans. Each core workstream has its own group.
Responsibilities | Agrees benefits and tracks them through the benefits register Agrees roles, resources and the programme plan Approves the pharmacy technician business case Manages red risks and issues and escalations Champions the programme with the Clinical Group | Checks delivery against the plan Reviews the RAID log and dependencies Agrees actions and logs decisions Shares learning and celebrates wins | Gives feedback on changes before they are tested Plans PDSA tests on the wards Brings the views of ward staff, patients and partners Carries news back to their teams
Inputs | Leadership report Benefits register (monthly) | Highlight reports from each workstream RAID log | Ward data and PDSA results
Outputs | Actions, decisions and escalations | Actions, decisions and escalations | Actions, decisions and escalations
Attendees | Chair: Dr Amara Okafor (SRO) Tom Reid, Priya Nair, James Holloway Workstream leads, Ruth Adeyemi (PMO) | Chair: James Holloway Workstream leads and CITI support Omar Siddiqui (data), Ruth Adeyemi (PMO) | Workstream leads, ward champions Partners as needed (pharmacy, transport, social work)
Governance
V1 October 2022