## Plan
ACTIVITY PLAN (2 March 2026 - 5 June 2026) Discharge Flow Programme |  |  |  | WC - start of programme overview: |  |  | 2026-03-02 | Overall completion: |  |  |  | March |  |  |  |  | April |  |  |  | May
James Holloway |  |  |  | Predicted programme completion date: |  |  | 2026-06-05 |  |  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Type | Activity | Description | Responsible | Start date | Days | Due date | Status | % complete | Critical Path (Y/N) | Comments | Todays date
Workstream | 1 | Board rounds and criteria-led discharge | Dr Sofia Marquez | 2026-03-02 | 70 | 2026-06-05 | In progress |  | Y
Activity | 1.1 | Agree the board round standard with Wards 5 and 6 | Dr Sofia Marquez | 2026-03-02 | 20 | 2026-03-27 | COMPLETE | 100% | Y | 2 weeks late: ward manager leave
Sub-activity | 1.1.1 | Observe 4 board rounds on each ward | Ben Carter | 2026-03-02 | 10 | 2026-03-13 | COMPLETE | 100% | N
Sub-activity | 1.1.2 | Run PDSA tests of the 30-minute board round | Joy Adebayo | 2026-03-16 | 10 | 2026-03-27 | COMPLETE | 100% | Y | 3 PDSA cycles
Activity | 1.2 | Criteria-led discharge policy through Clinical Governance | Dr Sofia Marquez | 2026-03-23 | 25 | 2026-04-24 | COMPLETE | 100% | N | Approved 24/04
Activity | 1.3 | Spread the board round to Wards 1 to 4, 7 and 8 | Joy Adebayo | 2026-03-30 | 50 | 2026-06-05 | In progress | 75% | Y | 6 of 8 wards live
Milestones | 1.4 | Board round live on all 8 wards | Grace Mensah | 2026-06-05 | 1 | 2026-06-05 | Not started | 0% | Y
Workstream | 2 | Medicines to take out (TTOs) | Leila Haddad | 2026-03-02 | 70 | 2026-06-05 | In progress |  | Y
Activity | 2.1 | Agree the TTO process for the day before discharge | Leila Haddad | 2026-03-02 | 30 | 2026-04-10 | COMPLETE | 100% | N
Activity | 2.2 | Recruit 2 pharmacy technicians | Leila Haddad | 2026-03-16 | 35 | 2026-05-01 | COMPLETE | 100% | Y | Started 05/05
Activity | 2.3 | Build the daily TTO tracker | Omar Siddiqui | 2026-03-23 | 45 | 2026-05-22 | In progress | 60% | N | Ward codes issue I-002
Activity | 2.4 | Spread TTO the day before to all 8 wards | Arjun Mehta | 2026-04-20 | 35 | 2026-06-05 | In progress | 40% | Y | Rota gaps on Wards 1 to 4
Workstream | 3 | Transport and discharge lounge | Kwame Asante | 2026-03-09 | 60 | 2026-05-29 | In progress |  | N
Activity | 3.1 | Agree 4 more morning transport slots | Kwame Asante | 2026-03-09 | 25 | 2026-04-10 | COMPLETE | 100% | N
Activity | 3.2 | Open the lounge at 8am | Kwame Asante | 2026-03-23 | 29 | 2026-04-30 | COMPLETE | 100% | N | Opened 30/04
Activity | 3.3 | Promote the lounge at ward huddles | Chloe Evans | 2026-05-04 | 20 | 2026-05-29 | In progress | 50% | N
Workstream | 4 | Complex discharges | Fiona Gallagher | 2026-03-09 | 55 | 2026-05-22 | In progress |  | N
Activity | 4.1 | Start the daily transfer of care huddle | Fiona Gallagher | 2026-03-09 | 26 | 2026-04-13 | COMPLETE | 100% | N | Live 13/04
Activity | 4.2 | Plan the discharge to assess pilot | Sam Patel | 2026-04-20 | 25 | 2026-05-22 | In progress | 50% | N
Workstream | 5 | Data and measurement | Omar Siddiqui | 2026-03-02 | 60 | 2026-05-22 | In progress |  | Y
Activity | 5.1 | Agree baseline and data definitions | Omar Siddiqui | 2026-03-02 | 10 | 2026-03-13 | COMPLETE | 100% | Y
Activity | 5.2 | Weekly SPC dashboard for each ward | Omar Siddiqui | 2026-03-16 | 50 | 2026-05-22 | In progress | 80% | N
Workstream | 6 | PMO, comms and engagement | Ruth Adeyemi | 2026-03-02 | 60 | 2026-05-22 | In progress |  | N
Activity | 6.1 | Launch event and ward roadshows | Nadia Rahman | 2026-03-02 | 30 | 2026-04-10 | COMPLETE | 100% | N
Meeting | 6.2 | Programme Leadership Meeting (fortnightly) | Ruth Adeyemi | 2026-03-02 | 60 | 2026-05-22 | In progress | 85% | N
Activity | 6.3 | Patient leaflet with the patient panel | Nadia Rahman | 2026-05-04 | 15 | 2026-05-22 | In progress | 30% | N